## Worksheet
LOGBOOK SYSTEM
Unit | Main Category | Sub System | Date/Time Performed | Date Done | Done By | Due Date | Notes | Performed By | Logged By | Logged Date | Status
DG5 | Main Engine | Cylinder Head | 2018-02-05 07:00 | 2018-04-12 08:59:21 | Beverly Ampog |  | Continue cleaning/painting of bonnet and cover. Note: Prepared by: Torrijos | Beato, Montero,Urnopia, Anacay, Lovico, Bawar, Elmer, Plarisan, Erimar, Pintason, Jaronay, Stewart | Beverly Ampog | 2018-04-12 08:59:21 | Done
DG5 | Ancillary and Auxiliary | Starting & Control Air System | 2018-02-05 07:00 | 2018-04-12 08:56:53 | Beverly Ampog |  | Installed master valve Air Starting. Note: Prepared by: Torrijos | Beato, Montero,Urnopia, Anacay, Lovico, Bawar, Elmer, Plarisan, Erimar, Pintason, Jaronay, Stewart | Beverly Ampog | 2018-04-12 08:56:53 | Done
DG5 | Ancillary and Auxiliary | Filtration System | 2018-02-05 19:00 | 2018-04-12 09:07:13 | Beverly Ampog |  | Servicing of check filter and Y-strainer of LO flushing line. | Alevio, Canama, Labanon, Corino, Alila, M. Noman, Muralla, Lobrido, A. Noman | Beverly Ampog | 2018-04-12 09:07:13 | Done
DG5 | Others | Others | 2018-02-05 07:00 | 2018-04-12 09:01:07 | Beverly Ampog |  | Start flushing header pipe to tank. Note: Prepared by: Torrijos | Beato, Montero,Urnopia, Anacay, Lovico, Bawar, Elmer, Plarisan, Erimar, Pintason, Jaronay, Stewart | Beverly Ampog | 2018-04-12 09:01:07 | Done
DG5 | Others | Others | 2018-02-05 19:00 | 2018-04-12 09:04:18 | Beverly Ampog |  | Continue working at platform between Engine catwalk and 2nd floor. | Alevio, Canama, Labanon, Corino, Alila, Noman, Muralla, Lobrido, Noman | Beverly Ampog | 2018-04-12 09:04:18 | Done
DG5 | Main Engine | Crankshaft | 2018-02-06 07:00 | 2018-04-12 09:14:20 | Beverly Ampog |  | Continue flushing line to crankshaft. Note: Prepared by: Torrijos | Beato, Urnopia, Montero, Anacay, Lovico, Bawar, Elmer, Plarisan, Jaronay, Pintason, Erimar | Beverly Ampog | 2018-04-12 09:14:20 | Done
DG5 | Main Engine | Turbo Charger | 2018-02-06 14:00 | 2018-04-12 09:19:42 | Beverly Ampog |  | Cleaning of Turbo charger gas inlet casing. | Alevio, Canama, Labanon, Corino, M. Noman, Alila, A. Noman, Lobrido, Muralla | Beverly Ampog | 2018-04-12 09:19:42 | Done
DG5 | Main Engine | Turbo Charger | 2018-02-06 22:00 | 2018-04-12 09:29:23 | Beverly Ampog |  | Cleaning/removal of old paint of gas inlet casing. Application of rust converter and primer paint. Note: Prepared by: Ortega | Corino, Canama, Labanon, Alevio, M. Noman, Alila, Muralla, Lobrido, A. Noman | Beverly Ampog | 2018-04-12 09:29:23 | Done
DG5 | Main Engine | Inter Cooler | 2018-02-06 22:00 | 2018-04-12 09:26:53 | Beverly Ampog |  | Fabrication of railings Air cooler area. Note: Prepared by: Ortega | Corino, Canama, Labanon, Alevio, M. Noman, Alila, Muralla, Lobrido, A. Noman | Beverly Ampog | 2018-04-12 09:26:53 | Done
DG5 | Electric Generator | Exciter | 2018-02-06 07:00 | 2018-04-12 09:15:20 | Beverly Ampog |  | Relocation of Exciter. Note: Prepared by: Torrijos | Beato, Urnopia, Montero, Anacay, Lovico, Bawar, Elmer, Plarisan, Jaronay, Pintason, Erimar | Beverly Ampog | 2018-04-12 09:15:20 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-06 14:00 | 2018-04-12 09:20:48 | Beverly Ampog |  | Continued monitoring of Lube oil flushing. | Alevio, Canama, Labanon, Corino, M. Noman, Alila, A. Noman, Lobrido, Muralla | Beverly Ampog | 2018-04-12 09:20:48 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-06 22:00 | 2018-04-12 09:31:17 | Beverly Ampog |  | Continue flushing of lube oil line to crankshaft. Note: Prepared by: Ortega | Corino, Canama, Labanon, Alevio, M. Noman, Alila, Muralla, Lobrido, A. Noman | Beverly Ampog | 2018-04-12 09:31:17 | Done
DG5 | Others | Others | 2018-02-06 07:00 | 2018-04-12 09:17:02 | Beverly Ampog |  | Continue cleaning of Engine parts. Note: Prepared by: Torrijos | Beato, Urnopia, Montero, Anacay, Lovico, Bawar, Elmer, Plarisan, Jaronay, Pintason, Erimar | Beverly Ampog | 2018-04-12 09:17:02 | Done
DG5 | Others | Others | 2018-02-06 14:00 | 2018-04-12 09:23:50 | Beverly Ampog |  | - Continued cleaning of Engine parts/accessories. - Preparation/fabrication of railings at newly installed platform beside air cooler are (L/R). | Alevio, Canama, Labanon, Corino, M. Noman, Alila, A. Noman, Lobrido, Muralla | Beverly Ampog | 2018-04-12 09:23:50 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-07 07:00 | 2018-04-12 09:35:59 | Beverly Ampog |  | Continue circulation of flushing oil crankshaft to line. Note: Prepared by: Torrijos | Beato, Montero, Anacay, Lovico, Bawar, Elmer, Plarisan, Pintason, Jaronay, Liaquen | Beverly Ampog | 2018-04-12 09:35:59 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-07 14:00 | 2018-04-12 09:37:22 | Beverly Ampog |  | Cleaning of oil pan. | Alevio, Canama, Labanon, Corino, M. Noman, Muralla, A. Noman | Beverly Ampog | 2018-04-12 09:37:22 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-07 22:00 | 2018-04-12 09:44:07 | Beverly Ampog |  | Servicing of drip pump. Note: Prepared by: Ortega | Corino, Labanon, Canama, Alevio, M. Noman, A. Noman, Muralla | Beverly Ampog | 2018-04-12 09:44:07 | Done
DG5 | Ancillary and Auxiliary | Lube oil System | 2018-02-07 22:00 | 2018-04-12 09:48:25 | Beverly Ampog |  | Servicing of Lube oil circulating pump. Note: Prepared by: Ortega | Corino, Labanon, Canama, Alevio, M. Noman, A. Noman, Muralla | Beverly Ampog | 2018-04-12 09:48:25 | Done
DG5 | Others | Others | 2018-02-07 07:00 | 2018-04-12 09:33:48 | Beverly Ampog |  | Continue cleaning/priming of Engine parts and accessories. Note: Prepared by: Torrijos | Beato, Montero, Anacay, Lovico, Bawar, Elmer, Plarisan, Pintason, Jaronay, Liaquen | Beverly Ampog | 2018-04-12 09:33:48 | Done
DG5 | Others | Others | 2018-02-07 14:00 | 2018-04-12 09:39:33 | Beverly Ampog |  | - Continued cleaning/priming of Engine parts and accessories. - Preparation/fabrication of railing for steel ladder at RB side. | Alevio, Canama, Labanon, Corino, M. Noman, Muralla, A. Noman | Beverly Ampog | 2018-04-12 09:39:33 | Done
DG5 | Others | Others | 2018-02-07 22:00 | 2018-04-12 09:42:57 | Beverly Ampog |  | - Cleaning/painting of Engine parts/accessories. - Fabrication of hand rail for steel ladder. Note: Prepared by: Ortega | Corino, Labanon, Canama, Alevio, M. Noman, A. Noman, Muralla | Beverly Ampog | 2018-04-12 09:42:57 | Done
DG5 | Main Engine | Turbo Charger | 2018-02-08 14:00 | 2018-04-12 09:54:14 | Beverly Ampog |  | Temporary installation of LB turbo charger gas inlet casing. | Alevio, Canama, Labanon, Corino, Urnopia, A. Noman, Muralla, Lobrido | Beverly Ampog | 2018-04-12 09:54:14 | Done
DG5 | Others | Others | 2018-02-08 14:00 | 2018-04-12 09:52:08 | Beverly Ampog |  | - Continued cleaning/priming of Engine parts and accessories. - Continued installation of catwalk railings. | Alevio, Canama, Labanon, Corino, Urnopia, A. Noman, Muralla, Lobrido | Beverly Ampog | 2018-04-12 09:52:08 | Done
DG5 | Others | Others | 2018-02-08 22:00 | 2018-04-12 09:57:13 | Beverly Ampog |  | - Continued cleaning/painting of Engine parts and accessories. - Continued installation of catwalk railings turbo charger side. Note: Prepared by: Ortega | Corino, Labanon, Urnopia, Canama, Alevio, A. Noman, Lobrido, Muralla | Beverly Ampog | 2018-04-12 09:57:13 | Done
DG5 | Main Engine | Counter Weight | 2018-02-09 07:00 | 2018-04-12 10:00:30 | Beverly Ampog |  | - Marking of counter weight and pin. - Loosening of balance weight #4. Note: Prepared by: Torrijos | Beato, Anacay, Lovico, Bawar, Elmer, Plarisan, Pintason, Jarunay, Stewart, Erimar, Marvin | Beverly Ampog | 2018-04-12 10:00:30 | Done
DG5 | Main Engine | Counter Weight | 2018-02-09 14:00 | 2018-04-12 10:12:35 | Beverly Ampog |  | Pulled out CW #3 and CW #4. | Alevio, Labanon, Montero, Corino, Urnopia, Muralla, A. Noman | Beverly Ampog | 2018-04-12 10:12:35 | Done
DG5 | Others | Others | 2018-02-09 07:00 | 2018-04-12 10:09:00 | Beverly Ampog |  | - Fabricate stand for long handle socket square. - Continue cleaning Engine parts and accessories and painting primer. Note: Prepared by: Torrijos | Beato, Anacay, Lovico, Bawar, Elmer, Plarisan, Pintason, Jarunay, Stewart, Erimar, Marvin | Beverly Ampog | 2018-04-12 10:09:00 | Done
DG5 | Others | Others | 2018-02-09 14:00 | 2018-04-12 10:11:47 | Beverly Ampog |  | Continued cleaning/painting priming of Engine parts and accessories. | Alevio, Labanon, Montero, Corino, Urnopia, Muralla, A. Noman | Beverly Ampog | 2018-04-12 10:11:47 | Done
DG5 | Main Engine | Crankshaft | 2018-02-10 22:00 | 2018-04-12 10:20:28 | Beverly Ampog |  | Cleaning crankshaft. Note: Prepared by: Ortega | Beato, Urnopia, Montero, A. Noman, Plarisan, Liaquen | Beverly Ampog | 2018-04-12 10:20:28 | Done
DG5 | Main Engine | Counter Weight | 2018-02-10 14:00 | 2018-04-12 10:15:44 | Beverly Ampog |  | Pulled out balance weight, #1 - 150 bars. | Beato, Urnopia, Montero, Plarisan, Liaquen, A. Noman | Beverly Ampog | 2018-04-12 10:15:44 | Done
DG5 | Main Engine | Counter Weight | 2018-02-10 22:00 | 2018-04-12 10:18:28 | Beverly Ampog |  | *Pulled out balance weight #2 - 100 bars. *Cleaning/marking of balance weight, jacking bolt and locking plate. Note: Prepared by: Ortega | Beato, Urnopia, Montero, A. Noman, Plarisan, Liaquen | Beverly Ampog | 2018-04-12 10:18:28 | Done
DG5 | Ancillary and Auxiliary | Fuel System | 2018-02-10 22:00 | 2018-04-12 10:22:50 | Beverly Ampog |  | Checking clearance of fuel cam base circle and fuel pump roller drive. Note: Prepared by: Ortega | Beato, Urnopia, Montero, A. Noman, Plarisan, Liaquen | Beverly Ampog | 2018-04-12 10:22:50 | Done
DG5 | Main Engine | MB Shell | 2018-02-12 14:00 | 2018-04-12 10:27:56 | Beverly Ampog |  | Cleaning/polishing of Main Bearing #1 bearing body. Note: Prepared by: Ortega | Beato, Urnopia, Montero, Plarisan, Jabiniar, Liaquen, Pintason, Jaronay | Beverly Ampog | 2018-04-12 10:27:56 | Done
DG5 | Others | Others | 2018-02-12 14:00 | 2018-04-12 10:30:37 | Beverly Ampog |  | Continue fabrication of side wall cover of Engine platform generator side. Note: Prepared by: Ortega | Beato, Urnopia, Montero, Plarisan, Jabiniar, Liaquen, Pintason, Jaronay | Beverly Ampog | 2018-04-12 10:30:37 | Done
DG5 | Main Engine | Cylinder Head | 2018-02-13 14:00 | 2018-04-12 10:35:35 | Beverly Ampog |  | - Polishing of Cylinder liner landing contact surfaces. - Servicing of tension jack, replaced packing. Cyl liner cleaning: CL 24, CL 07. Note: Prepared by: Ortega | Beato, Urnopia, Montero, Plarisan, Jabiniar, Liaquen, Jaronay, Pintason | Beverly Ampog | 2018-04-12 10:35:35 | Done
DG5 | Main Engine | Cylinder Head | 2018-02-13 22:00 | 2018-04-12 10:41:41 | Beverly Ampog |  | - Cleaning of Engine landing surface at Cyl # 1 to 18. Preparation for installation of JW/liner. - Cleaning JW/liner preparation for installation , Cyl liner # 20, 3022, 3003, 3026, 32, 3030. | Urnopia, Montero, Plarisan, Erimar, Liaquen, Pintason, Jaronay | Beverly Ampog | 2018-04-12 10:41:41 | Done
DG5 | Others | Others | 2018-02-13 14:00 | 2018-04-12 10:37:04 | Beverly Ampog |  | Fabrication of side wall door of Engine platform Generator side B-bank. Note: Prepared by: Ortega | Beato, Urnopia, Montero, Plarisan, Jabiniar, Liaquen, Jaronay, Pintason | Beverly Ampog | 2018-04-12 10:37:04 | Done
DG5 | Main Engine | Cylinder Head | 2018-02-14 14:00 | 2018-04-12 10:45:51 | Beverly Ampog |  | Cleaning JW liner preparation for Cyl liner installation, JW liner # 1061, JW liner # 1030, JW liner # 1055. Note: Prepared by: Ortega | Montero, Plarisan, Jabiniar, Liaquen, Pintason, Jaronay | Beverly Ampog | 2018-04-12 10:45:51 | Done
DG5 | Ancillary and Auxiliary | Cooling System | 2018-02-14 22:00 | 2018-04-12 10:50:56 | Beverly Ampog |  | Continue cleaning JW liner preparation for installation, JW liner #405, JW liner #1092. | Montero, Plarisan, Erimar, Liaquen, Jaronay, Pintason | Beverly Ampog | 2018-04-12 10:50:56 | Done
DG5 | Others | Others | 2018-02-14 14:00 | 2018-04-12 10:48:15 | Beverly Ampog |  | Continued fabrication of side wall door Engine platform Generator side. Note: Prepared by: Ortega | Montero, Plarisan, Jabiniar, Liaquen, Pintason, Jaronay | Beverly Ampog | 2018-04-12 10:48:15 | Done
DG5 | Others | Others | 2018-02-14 22:00 | 2018-04-12 10:52:10 | Beverly Ampog |  | Continued fabrication of side wall door Engine platform generator side. | Montero, Plarisan, Erimar, Liaquen, Jaronay, Pintason | Beverly Ampog | 2018-04-12 10:52:10 | Done
DG5 | Main Engine | MB Shell | 2018-02-15 07:00 | 2018-04-12 11:01:51 | Beverly Ampog |  | *MB #1: -Loosening of bearing saddle/cap for inspection. -Reinstallation of main bearing cap/saddle. *Main bearing saddle torque: -Lateral bolts right initial, Ok. -Tie rod bolt final torque, Ok, Left is 640 bars and Right is 680 bars. -Lateral bolt right final 180 bars. -MB #1 cap jack bolts 840 bars. -Brand new bearing. Note: Prepare by: Torrijos | Beato, Labanon, Urnopia, Corino, Ortega, Bawar, Lovico, Anacay, Marvin, Alvin, Lobrido, Muralla | Beverly Ampog | 2018-04-12 11:01:51 | Done
DG5 | Main Engine | MB Shell | 2018-02-16 07:00 | 2018-04-12 11:13:15 | Beverly Ampog |  | *Re-hand tapping of Cylinder jacket bolt holes. *MB #2: -Lowered MB #2 saddle and cap. -Loosening pressure: MB cap jack bolts = 800 bars, Tie rod loosening RB = 650 bars and LB = 670 bars. *MB #4: -Lowered MB #4 cap and saddle. -Loosening pressure: MB cap jack bolts = 800 bars, Tie rod loosening LB = 590 bars and RB = 600 bars. *MB #2 and 4 Crack test main bearing saddle and cap, Ok. Note: Prepared by: Torrijos | Beato, Corino, Urnopia, Bawar, Ortega, Dante, Erimar, Plarisan, Pintason, Liaquen, Jaronay, Alvin, Alila | Beverly Ampog | 2018-04-12 11:13:15 | Done
DG3 | Main Engine | MB Shell | 2018-04-17 12:12 | 2018-04-18 02:59:00 | Admin | 2018-04-20 | asdasd | sadasd | Admin | 2018-04-17 14:07:45 | Done
DG1 | Main Engine | Crankshaft | 2018-04-18 12:12 | 2018-04-18 03:01:22 | Admin | 2018-04-20 | asdddsa | asdsda | Admin | 2018-04-18 09:00:38 | Done
DG1 | Main Engine | Counter Weight | 2018-04-18 12:12 | 2018-04-18 03:02:52 | Admin | 2018-04-21 | dadsa | sadsadsd | Admin | 2018-04-18 09:02:18 | Done
DG3 | Main Engine | Crank Pin Bearing Shell | 2018-04-18 12:12 | 2018-04-17 14:11:30 | Admin | 2018-04-23 | sadasd | sadsadasdsad | Admin | 2018-04-17 14:11:30 | Done
DG1 | Instrumentation and Control | Metering | 2018-04-18 12:12 | 2018-04-18 09:15:38 | Admin | 2018-04-20 | agay | agay | Admin | 2018-04-18 09:14:45 | Done
UPDATES: |  |  | 2018-04-18 12:12 |  |  |  | asdsda | sadsad | Admin | 2018-04-18 09:17:40 | On-Progress
UPDATES: |  |  | 2018-04-18 12:12 |  |  |  | dsasd | sdaasd | Admin | 2018-04-18 09:17:58 | Done
DG2 | Instrumentation and Control | Switchgear | 2018-04-18 12:12 | 2018-04-18 02:48:30 | Admin | 2018-04-19 | sdasdasd | dsaasd | Admin | 2018-04-18 08:40:16 | Done
DG1 | Main Engine | Engine Frame | 2018-04-19 12:12 | 2018-04-18 02:56:50 | Admin | 2018-04-21 | asda | sadsad | Admin | 2018-04-18 08:56:12 | Done
DG3 | Main Engine | MB Shell | 2018-04-19 12:12 | 2018-04-18 02:40:35 | Admin | 2018-04-21 | asdsd | sadasd | Admin | 2018-04-17 14:09:56 | Done
DG1 | Main Engine | Counter Weight | 2018-04-23 12:12 | 2018-04-23 08:48:12 |  | 2018-04-25 | asas | stephine | Admin | 2018-04-23 08:48:12 | On-Progress